## Sheet1
Task | SubTask | Hours
Edit Distances
| Wagner-Fischer implementation | 1
| Wagner-Fischer Unit Tests | 0.5
Program to be configurable
| Configuration Feature implememtation | 0.5
Resource Manager
| Architecture | 4
| Architecture Review | 2
Intial Election
| Initial election - implementation | 4
| Initial election - unit tests | 2
New Election by new process
| Request new election implementation | 2
| Request new election implementation | 1
Election from Failure
| Failure detection - implementation | 2
| Failure detection - Unit test | 1
Master to create Work Queue
| Master to detect work - implemenation | 1
| Master to detect work - unit test | 1
Request work
| Request Work - Implementation | 1
| Request Work - Unit Test | 1
| Terminate on no work left | 0.1
| Terminate on no work left - unit test | 0.5
Report completed work
| Report ability - implementation | 1
| Report ability - implementation | 1
Ability to terminate safely (worker)
| Ablity to terminate - implementation | 1
| Ablity to terminate - unit tests | 1
Requeue work on failure
| Master to detect worker failure | 1
| Master to detect worker failure | 1
Worker to requeue work on shutdown
| Master to detect worker failure | 1
| Master to detect worker failure | 1
Ability to terminate safely (Master)
| Implementation | 1
| Unit Tests | 1
Folder structure
| Code out building folder structure | 1
| Code out building folder structure unit tests | 1
Logging
| Implement Log4Net | 0.5
| Continued logging throughout | 2
Debugging |  | 8
| Expected Dev time | 47.1
EC2 / S3 - First machine setup
| Setup first machine | 3
| Install dependencies | 0.5
| Install program | 0.5
EC2 / S3 - Test 1
| Test | 0.25
| Analyze test | 0.25
EC2 / S3 - Test 2
| Test | 0.25
| Analyze test | 0.25
EC2 / S3 - Test 3
| Spin up 7 more machines | 0.15
| Script to launch process on 8 machines at the same time | 2
| Test | 0.25
| Analyze test | 0.25
EC2 / S3 - Test 4
| Test | 0.25
| Analyze test | 0.25
EC2 / S3 - Test 5
| Test | 0.25
| Analyze test | 0.25
EC2 / S3 - Test 6
| Test | 0.25
| Analyze test | 0.25
| Test Time | 9.15
| Report time | 2.5
| Total Time | 58.75